## MIESTONES
CONTROL
|  | 19th SEPTEMBER |  |  | 12th SEPTEMBER |  |  | 5th SEPTEMBER | 4th Sept | 3rd Sept | 2nd Sept | 29th AUGUST | 28th August | 27th August
DASHBOARDS |  |  |  |  | Store Level |  |  | Credentials to Client | Corporate |  | Marketing
DATA set up | [5 empty] | FREEDOM |  | NCR
[8 empty] | Freedom Pay | PIXEL
DATA RE ORG - ELJAY | [6 empty] | Audience Sets w Enriched Data | Purchase Triggers w Preferences
PUBLICATIONS |  |  | Google API |  | META - API |  |  |  | SMS | EMAIL
SEGMENT - Publication
[6 empty] | First Flight ADS - |  | SCALE Campaign w Data |  | Sample Email Campaign
AI ML Model | [7 empty] | Active Publication |  |  | Client Lists by Propensity | Internal Training
CREATIVE | [6 empty] | Email Distribution | 1 click buy | Email Distribution Tests |  | Ad Creation Module | Asset manager - internal training
[7 empty] | LTV MODULE | AI MODULE | Ad tagging - w builder |  | Client Training
[10 empty] | First Creative Library |  | Ad Creation Module - staging
E COMMERCE |  |  |  | 1 CLICK BUY | LTV Growth MODULE
IN Store | QR Code
Mongo DB Transition
Asset manager - internal training

## TASK FLOW
|  |  | DATA | [5 empty] | MEDIA /Publication | [5 empty] | E COMMERCE |  |  |  | RESBYTE.AI
|  |  | Ingestion |  |  |  | transformation | Presentation | Emailers | MMS | Meta |  | Google | CTV ( Tradedesk) | Code Only Set up- Delivery | Code Only Set up- Instore | Landing Page Set up | Instore Set up | Site Language / text | USER Permisions
[11 empty] | Insta | Facebook |  |  |  |  | w OLO
| NCR |  | Web Hook |  |  |  | Consumer IDS Resolution | Sigma -STOR | [6 empty] | Fishbowl Codes | Fishbowl/NCR |  |  | Review all pages
| Freedom Pay | [5 empty] | Consumer ID s enrichment | Presentation Interruptions | [10 empty] | AI Loyalty Page
customer id data
| Olo | [17 empty] | LTV Growth Page
| delivery data | [6 empty] | Store View
| Thankx |  | API Set up
E coom , loyalty, app
| Kanopi |  | Acuity Pixel Set up
| NCR |  | Web hook from NCR to SF | Jason | 2025-10-17
Freedom Pay
|  |  | API Set up | Brian | ??
| Thankx |  | Data Transfer | Patrick | 2025-10-18
|  |  | API Set up | Brian
| KANOPI |  | Pixel Details to Acuity | Jason | 2025-10-18
|  |  | Pixel from Acuity | PT | 2025-10-24
|  |  | Pixel to Lamad- Patrick | Brian | 2025-10-25
|  |  | Pixel installed and tested | Jason | 2025-10-30
DATA TRANSFORMATION
|  |  | Consumer IDS Resolution-Process Tests | Jason | 2025-10-18
|  |  | Data Run | TBD | 2025-10-22
|  |  | Data Enrichment | TBD | 2025-10-25
PRESENTATION
|  |  | Data Flow | Jason/Pritplal | 2025-10-21
( presentation layer interruptions )_
STORE VIEW
|  |  | Design | PT | 2025-10-22
|  |  | Front End Set up | Suntech ? | 2025-10-31
|  |  | Permissions | Suntech | 2025-10-25
|  |  | Permissions Module Test | ?? | 2025-10-22
SIGMA-STOR
|  |  | Design | PT | 2025-10-31
|  |  | Desgn - React | Suntech ( ?) | 2025-11-07
|  |  | Stored Procedures | Jason | 2025-11-14
I132C92C92:I135 | MEDIA
| Emailers |  | Set up and Testing | Jason | 2025-10-21
|  |  | Design | PT | 2025-10-22
|  |  | Template Imntegration | Suntech | 2025-10-23
|  |  | Cluster Set up | Jason | 2025-10-22
|  |  | Content Library | Suntech ? | 2025-10-23
|  |  | Content Verification | Kristin | 2025-10-22
| MMS |  | Set up and tested | Jason | 2025-10-21
|  |  | Design | PT | 2025-10-22
|  |  | Template Imntegration | Suntech | 2025-10-23
|  |  | Cluster Set up | Jason | 2025-10-22
|  |  | Content Library | Suntech | 2025-10-21
| Meta |  | API Set up | Matthias ( ?) | 2025-10-17 | Decision
Insta
| Facebook |  | API Test Date |  | 2025-10-30
| Google |  | API launch date |  | 2025-11-07
| CTV ( Tradedesk) |  | TBD
ECOMMERCE
Code Only Set up
| Fishbowl codes |  | Codes set up in templates | Jason | 2025-10-18
| Instore Set up | Brian- Patrick | Codes - Fishbowl/NCR | PT to set up | 2025-10-21
| OLO - Integration |  | Follow up call for permission | PT - BRIAN | 2025-10-18
RESBYTE.AI WEB SITE Mgmnt
| Site Language / text |  |  | PT | 2025-10-25
Review all pages
|  |  | AI Loyalty Page | PT
|  |  | LTV Growth Page | PT
|  |  | Site Management -uptimne | Prokopto | 2025-10-25
|  |  | Payment / Invoicing | TBD
USER PERMISSION s
|  |  | Admin Module | Suntech | 2025-10-21
|  |  | Testing | TBD | 2025-10-21

## TASKS
| PENDING TASKS LIST |  | updated 251014
| DATA | [6 empty] | E Commerce |  |  | Marketing Mgmnt |  |  |  |  | ADMIN
Data Dashboards
D1 |  |  | Sigma- Sales number show - July data |  |  |  |  | E1 | Landing Pages w Items - Dynamic |  | M1 | Audience set up w past purchase | 265k | DataEng to confirm | A1 | User Name / pswrds for Corporate
D2 |  |  | Segments- Uncertain if all segments are updating |  |  |  |  | E2 | Integration with OLO | call at 4 PM EST | M2 | Emails set up in Profiles | AI Agent Sorting | Jason to confirm | A2 | Store level access set up
D3 |  |  | Segments- First Time customer segments- PIXEL iNstalation on Web site - |  |  |  |  | E3 | Coupon at NCR | call w PATRICK _ expected 10/15 | M3 | Behavioral triggers | AI Agent logic | to be discussed | A3 | 24/7 support - | Prokopto set up and testing
[6 empty] | Pixel from Acuity |  | E5 |  |  | M4 | MMS set up | Jason to confirm
End point to Acuiity to build a pixel
[7 empty] | Q reg parameters |  |  |  | M5 | MMS Template approvals | Kristion to confirm - 10/16
[11 empty] | M6 | META API Set up | Mathias to review back end
D4 |  |  | NCR- Web hook to get daily data flow into Snowflake ( S3) Resbyte
[11 empty] | M7 | Google API set up | Mathias to confirm after review
D5 |  |  | Freedom Pay - Historical Data dump
D6 |  |  | THANX data |  | go from daily dumps to live API
D7 |  |  | NCR-Freedom pay - data connectivity at source- Connect consumer data to actual transactions
D8 |  |  | Acuity | Data ID Resolution rates
D9 |  |  |  | Data Enrichment

## Sheet2
FINAL CHECKLIST
[6 empty] | Responsibility |  | Next Action |  | Sign off 1 |  | Sign Off 2
|  | 1 | Customer Access | Corporate |  |  |  | Jason to confirm
|  |  | Dashboards |  |  |  |  | usernames to Parminder - PT
|  | 2 | Asset Manager |  |  | Prminder |  | Seperation- primary- Add ons |  | Shashi |  | Jason
|  | 3 | Ad Creator Module |  |  | Jason |  | 1st Set of sample ads for LA mAd Templates creation |  | Rick |  | Jason
MENU - AD ONS
|  | 4 | Ad Generator |  |  | Shashi |  | Logic | ? | Price Logic | Pt
[10 empty] | Design logic | Jason
|  | 5 | Personalized Profile- content allocation |  |  |  |  | Provide Logic | PT |  | TODAY
[8 empty] | API | Jason
|  | 5 | Publishing Channels
|  |  |  | Email |  |  | Jason |  |  |  | Complete
|  |  |  | MMS |  |  | Jason |  |  |  | 19th Sept
|  |  |  | Meta |  |  | Joseph
|  |  |  | Google |  |  | Joseph |  | Test Kets
|  | 6 | Data
|  |  |  | NCR |  | Live | Jason
|  |  |  | Freedom |  |  | Patrick
|  |  |  | Olo |  | Live | Complete |  | Eljay ? | OLO - Full Data access
Thankx
|  |  |  | Acuity PIXEL | E comm |  | LAMAD |  | Data Destination |  | Jason
19th Sept
[5 empty] | Web Site |  | LAMAD
| 25th SEPT | 7 | PAYMENT
|  |  |  | STRIPE |  |  | Creds to Parminder |  |  | 2025-09-22 | PT | Parminder
Calc frm PT
|  | 8 | Invoicing Setup | ?? | Stripe + Email
|  |  | INFRA | Backups
|  |  |  | Packages instalation |  |  | PRITPAL to sign off |  |  | 19th Sept
DATA by Store
AI ML MODEL Demo

## JOSEPH
JOSEPH
15-17th
1 | Schema -Behavioral | Set up |  | Patrick
2 | Google/Meta API s |  | Client Access
3

## DELIVERABLES
| 5th SEPT | 9th SEPT |  | 10th SEPT | 12 th SEPT | 15th SEPT | 17th SEPT | 19th SEPT | 22ND SEPT | 24th SEPT | 26th SEPT | 30th SEPT
| Asset Manager w images | Images - Resized for Digital |  | AD Creation module | Audience Sets w 1- Time 2- value- 3 item 4- Id HASHTAGS | LTV GROWTH MODULE | first 100 ORDERS | AI Loyalty Module | Live Ads version | First 1000 customers - recovered |  | First 10,000 transactioms
|  |  |  | w BRAND GUIDELINES | EMAIL | functioning w Audience selection |  | functioning w Audience selection
Images without Background
|  |  |  | CREATIVE DELIVERY |  | 1st Campaigns
Emails
|  |  |  | SMS | 1 click Landing pages for conversion | Emails
SMS
Insta
FB Ads
Google Ads
LAMAD DELIVERABLES
Promo LOGIC
LTV Based discount
Capacity Based Discount
PIXELS
Web Site
E Comm
1 Click Buy Integration

## Sheet1
windows
|  | 71 | 14
| 2100000 | 71 | 29577.4648 | 14 | 2112.6761 | 0.1% | 2.1127 | 2100 | 30 | 63000 | 1890000
| 1000000 | 71 | 14084.507 | 140.8451 | 4225.3521
7 days | 1000000 |  |  | 10000 | 300000
30 days

## OBJECTIVES
OBJECTIVES |  | AUG 15th |  |  |  | 2025-08-22 |  |  |  | 3rd Sept
|  | Dashboards |  |  |  | 1st Flight Campaign |  |  |  | II nd Flight
|  |  | Daily Sales Performance |  |  | Delivery | 800000 | Latent custoers |  | High Value | Latent
|  |  | Segments | [6 empty] | Meta
Google
|  |  | Items | [6 empty] | email
[6 empty] | Email Server |  | Cold Email ? |  | SMS
Promos
Location
|  | DATA | Eljay- Jason ? |  | Eljay
| 1 | System Set up | Infra servers + back ups |  | Y |  |  |  |  | Publishing - API S
Meta
[6 empty] | Creative Module |  |  |  |  | Google
| 3 | Code transfer |  |  | Pritpal | AI - 1st cut
| 4 | Dashboards | DESIGN _ SIGMA / STOR |  | J rev | Tracking - Behavioral Dashboard |  |  | Joseph /jason
| 5 | PII | Full Enrichment w Acuity |  | Eljay | NCR _ Couponing Set up
Veraset
| 6 | Best Sellors |  |  | Eljay |  |  |  |  | 9 | Snowflake - Intel | 7 days
1 Click buy
| 7 | Promos |  |  | Eljay
| 2 | System Security | Username/passwords |  |  | AI Model | Lists
| 8 | Location Level Access | Corporate |  | Jason to OK
|  |  | w Local Data |  | Parminder

## AUGUST 15th
| DATA |  |  |  | DASHBOARDS | APP | AI ML | GEN AI
( Dtls next tab)
AUGUST 1-8th | NCR API |  | API access / Patrick 1 week |  | Segments | DESIGN Module | Propensity Phase I | Design Module content generation
| OLO |  | Live data / Historical | Patrick | Sales by Meal Type
| THANX |  | Live
| Freedom Pay |  | Live | PCI Compliance
Data warehouse access
| VeraSet |  | TEST
( Proximity Data )
| WEB SITE PIXEL |  | Installed on LA Mad
|  | Thanx | E Comm instalation
API
AUGUST 11-15th | NCR API |  | Historical Data |  | Voice Activation | Publishing Module
| OLO |  | Historical Data
THANX
| Freedom Pay |  | Historical
| VeraSet | LIVE
( Proximity Data )
APP PIXEL
AUGUST 17-22 | Transunion DATA | Live |  |  |  | NCR COUPONING MODULE INTEGRATION
Propensity Phase -II
AUGUST 24-29th

## AI ML
PHASE-I |  | AI ML Agent
| Level 1 | Identify customers with highest propensity to buy at certain time window ( 15 mins)
| Criteria | Meal Type
Time of purchase
Day of purchase
| Sub criteria | sort by/in order
SNOWFLKE INTELLIGENCE
|  | Frequency | highest # per month | [5 empty] | Ask Sigma
|  | Latency | Last=first
special
( iMatch w Active specials only)
PHASE-II
Map Behavior |  |  |  | Frequency | Value | Timing | Proximity | Interaction -digital
|  |  |  | typical Buying Behavior | Ave Value Per month- utlization % | Typical time of purchase | LocationVis A Store - time of day/ day of week | No of digital touchpoints
RANK BEHAVIOR amongst all customer base
CALCULATE BEST OFFER
CALC STORE CAPACITY UTLIZATION % | No of meals @ capacity
PHASE-III |  | AI DRIVEN ANALYSIS

## DATA
DATA
| I | ID Resolution
Match w Purchase
Freedom Pay
AI Tool to match Transaction w Profiles
| 2 | Daily Customers
High Value
New