## Commercial Proposal: FOSS-Based AI-Enabled CSMP
Cost Structure Assumptions:
- Currency: All figures are in United States Dollars (USD) for international benchmarking. Final contracts can be denominated in TTD.
- Pricing Model: Time & Materials (T&M) with a Not-to-Exceed (NTE) Cap for the MVP phase. This provides flexibility for agile development while ensuring budget predictability for MPAAI.
- Team Rates: Based on a blended offshore/onshore model, with senior resources commanding higher rates. Rates are competitive for high-quality FOSS engineering.
- Infrastructure: Estimates are for a cloud-hosted environment (e.g., AWS, compatible with the Caribbean region). On-premises infrastructure would involve significant capital expenditure (CapEx) not reflected here.

### 1. Cost Estimation: Minimum Viable Product (MVP)
#### 1.1 Implementation Services (32 Weeks)
This covers the entire human capital cost for designing, developing, testing, and deploying the MVP.
Role	Commitment	Estimated Man-Days	Blended Daily Rate (USD)	Total Cost (USD)
Project Manager	Full-time	128	$650	$83,200
Solution Architect	Full-time	128	$800	$102,400
Django Backend Developer (x2)	Full-time	256	$600	$153,600
React/React Native Developer (x2)	Full-time	256	$550	$140,800
UI/UX Designer	Part-time (50%)	64	$550	$35,200
DevOps Engineer	Part-time (50%)	64	$700	$44,800
AI/ML Engineer	Part-time (50%)	64	$750	$48,000
QA/Test Engineer	Full-time	128	$500	$64,000
Subtotal (Labor)		~1,088 days		$672,000

Other Cost Factors	Description	Cost (USD)
Project Management & Overhead	(15% of Labor) Tools, administration, reporting.	$100,800
Contingency	(10% of Labor) For scope refinement and unforeseen challenges.	$67,200
Third-Party Penetration Test	Independent security audit prior to go-live.	$25,000
Travel & Expenses (T&E)	For key workshops, UAT, and go-live support (2-3 trips).	$30,000
Subtotal (Other Costs)		$223,000

#### 1.2 Annual Infrastructure & Software (Year 1)
While the software is FOSS, the cloud infrastructure and managed services have costs.
Component	Specification	Estimated Monthly Cost (USD)	Estimated Annual Cost (USD)
Compute (Kubernetes Cluster)	6-8 vCPUs, 16-32GB RAM (Production + Staging)	$600	$7,200
Database (PostgreSQL)	Managed instance (e.g., AWS RDS), High Availability, 500GB storage	$450	$5,400
Object Storage (MinIO/S3)	2 TB for documents, images, backups	$100	$1,200
CDN & WAF	Content Delivery & Web Application Firewall (e.g., CloudFront)	$150	$1,800
Monitoring & Logging	Prometheus, Grafana, Loki/ELK Stack	$200	$2,400
Backup & Disaster Recovery	Automated snapshots and off-site backups	$100	$1,200
Domain & SSL Certificates	.gov.tt domain, wildcard SSL	$50	$600
Subtotal (Infrastructure)		~$1,650/month	$19,800

#### 1.3 MVP Cost Summary
Cost Category	Total Cost (USD)
Implementation Services (One-time)	$895,000
Infrastructure & Hosting (Year 1)	$19,800
Total MVP Investment (Year 1)	$914,800

Not-to-Exceed (NTE) Proposal for MVP Implementation: $895,000

### 2. Cost Estimation: Post-MVP & Ongoing Costs
#### 2.1 Annual Support & Maintenance (From Year 2 Onwards)
A retainer for ongoing support, minor enhancements, and security updates.
Service	Description	Annual Cost (USD)
Standard Support Pack	8x5 support with 4-hour response time for critical issues. / Security patching for OS, Django, PostgreSQL, and other FOSS components. / Minor bug fixes and performance tuning. / Up to 10 man-days for minor feature requests.	$95,000
Infrastructure Hosting	(As per Section 1.2)	$19,800
Total Annual Cost (Post-MVP)		$114,800

#### 2.2 Phase 2: Enhancement Packages (Optional)
These are fixed-price or T&M packages for major new functionality.
Enhancement Package	Description	Estimated Cost (USD)
Advanced AI & Analytics	Predictive routing, sentiment analysis, advanced Superset dashboards.	120,000−180,000
RPA Integration	Automate 5-10 key processes with n8n/Airflow (e.g., data entry, status updates to legacy systems).	80,000−120,000
Advanced Omnichannel	Integration with additional channels (WhatsApp Business API, social listening).	40,000−60,000

### 3. Total Cost of Ownership (TCO) Analysis: 5-Year View
This demonstrates the significant value of the FOSS model by comparing it to the high recurring license fees of a proprietary stack.
Year	FOSS-Based Solution (USD)	Proprietary Stack (Indicative - USD)
Year 1 (MVP)	$914,800 (Implementation + Infra)	~1,200,000(Implementation+∗∗300k+ in Annual Licenses**)
Year 2	$114,800 (Support + Infra)	~450,000(Support+∗∗300k+ in Annual Licenses**)
Year 3	$114,800 (Support + Infra)	~450,000(Support+∗∗300k+ in Annual Licenses**)
Year 4	$114,800 (Support + Infra)	~450,000(Support+∗∗300k+ in Annual Licenses**)
Year 5	$114,800 (Support + Infra)	~450,000(Support+∗∗300k+ in Annual Licenses**)
Total 5-Year TCO	$1,374,000	~$3,000,000

Key TCO Insight: The FOSS solution offers an estimated ~55% savings over 5 years, primarily by eliminating over $1.5 million in proprietary software license fees. The investment is shifted from perpetual, opaque licensing to transparent, value-added services and development.
### 4. Pricing & Payment Milestones
We propose linking payments to the successful delivery of key MVP milestones, aligning our incentives with MPAAI's project success.
Milestone	Payment Trigger	Percentage	Amount (USD)
Mobilization	Project Kick-off & Charter Sign-off	10%	$89,500
Design Sign-off	Approval of UX/UI & Technical Architecture	20%	$179,000
Core Platform Delivery	Successful UAT of Citizen Portal, Mobile App, and Case Management	40%	$358,000
Go-Live & Project Completion	Successful Production Deployment and MVP Sign-off	25%	$223,750
Post-Deployment Support	Completion of 6-Month Warranty/Hypercare Period	5%	$44,750
Total		100%	$895,000

Infrastructure costs would be invoiced monthly or annually in advance, directly from the cloud provider or through us as a managed service.

### Conclusion
This commercial proposal for a FOSS-based CSMP provides the Government of Trinidad and Tobago with a fiscally responsible, high-value path to digital transformation. The estimated MVP investment of $895,000 delivers a complete, secure, and scalable platform, with a total 5-year cost of ownership that is roughly half that of a proprietary equivalent.
This model ensures that public funds are invested in building sovereign capability and long-term sustainability, rather than perpetual license payments. We are prepared to refine these estimates based on more detailed technical discussions.